## Sheet1
Construction Schedule of Value Template
Project Name: | [5 empty] | Application No.
Project Manager: | [5 empty] | Application Date.
Project No: | [5 empty] | Period To:
Item No. | Work Description | Scheduled Value | Completed Work |  | Material Presents not in D or E | Total Material D+E+F | % Complete | Balance to Finish | Retainage
|  |  | Previous Application | This Period
1050 | Demolition | 4000 | 1000 |  |  | 1000 | 25% | 3000 | 100
1055 | Electirical | 5000 | 1500 | 2000 | 900 | 4400 | 88% | 600 | 440
Total |  | 9000 | 2500 | 2000 | 900 | 5400 | 60% | 3600 | 540
Notes
Lorem ipsum dolor sit amet, consectetuer adipiscing elit. Maecenas porttitor congue massa. Fusce posuere, magna sed pulvinar ultricies, purus lectus malesuada libero, sit amet commodo magna eros quis urna. Nunc viverra imperdiet enim. Fusce est. Vivamus a tellus.
Pellentesque habitant morbi tristique senectus et netus et malesuada fames ac turpis egestas. Proin pharetra nonummy pede. Mauris et orci.
https://www.schedulesbox.com/