## Bridge Construction Schedule
BRIDGE CONSTRUCTION SCHEDULE
BRIDGE NAME |  | OCT | NOV | DEC | JAN | FEB | MAR | APR | MAY | JUN | JUL
Project Manager: John Doe |  | 2022 | 2022 | 2022 | 2023 | 2023 | 2023 | 2023 | 2023 | 2023 | 2023
CONSTRUCT GIRDERS | Tension the strand
Cast the girder
Release the prestressing
Ship the girder to the bridge site
ERECT GIRDERS AT THE BRIDGE SITE | Erect girders onto permanent bearings
Remove temporary strands
Cast diaphragms
Lorem ipsum activity
CAST DECK | Cast the bridge deck
Drying and measuring
Deck composite with girders - confirm
Lorem ipsum activity
FINAL CONDITION W/O LIVE LOAD | Controlled load tests
Diagnostic load tests
Compare responses and calculated values
Lorem ipsum activity
FINAL CONDITION WITH LIVE LOAD | Installation of the railing system
Installation of an overlay
Opening the bridge to live load
Any user defined loading test
58%
76%
25%
100%
0%
0%
0%
0%
0%
0%
0%
0%
0%
0%
0%
0%
0%
0%
0%
0%

## ©
© TemplateLab.com